## Slide 1
Transition Framework Presentation

## Slide 2: Agenda
Transition Lifecycle
Transition Transformation Genre
Stages of Transition
Transition Risk Management
Transition Report & Tracking
Transition Governance Structure

## Slide 3: Transition Lifecycle
Analysis
Due-Diligence Phase
Transition Phase
Steady Transformation Phase
Transition Completion
  Initial Analysis of Infrastructure / Application landscape
  Customer Adoptability on change management, Outsourcing/ Offshoring etc.
  Existing Contract vendor’s termination clause
  Infrastructure / Application Landscape Base lining
  Infrastructure Optimization / Complexity base lining.
  Service Maturity base lining.
  Transition Planning / Timeline
  Knowledge Acquisition Management by Towers
  Pilot / Guided Support
  Stabilization Planning with check and balance for steady-state.
  Service Level based service delivery.
  Continual Improvement Plan
  Daily/Weekly/ Monthly service delivery assessment.
  Process/Procedure Documentations to be completed.
  Application of Transformational themes.
  Risk Mitigation plan to be transferred to Delivery.
  All the pending issues and escalations to be closed.
  CSAT Report
  Lesson Learned
  Customer Sign-off
  Delivery Sign-off
Risk Matrix
Transition Forecast
Risk Matrix
Issue Framework
Risk Matrix
Issue Framework
Stabilization Plan
Transformational Dashboard
Risk/Issue/Escalation Matrix
Lesson Learned.

## Slide 4: Transition Transformation Genre
Transformation Genre
Staff Augmentation/
Consulting
Augmenting the customer team by providing resources with specified skill sets and expertise
Custom Projects
Portions of work as custom project scope or one of engagement with time-bound completion.
Managed Services
GAVS owns end-to-end life cycle with contractually committed SLAs and metrics, accepts specific responsibilities and risks

## Slide 5: Due Diligence
Due Diligence Stage | Input | Output
Planning | RFP/Request for Due Diligence Proposal Response Inventory of IT infrastructure / Applications and contact details of the system owners Any information on the history of IT infrastructure and applications Upfront information on historic call volumes and support arrangements as well as the desired SLA would be beneficial | Due Diligence Plan & Approach Prioritized set of towers/ applications Templates DD Plan Risk Management Plan Data Collection Template As is Process Assessment Questionnaire
Execution | Due Diligence Plan & Approach Prioritized set of towers / applications | Due Diligence Report Revised estimation/commercials summary DD Master Data Issue, Risk & Assumptions Tracker Transition sequencing (waves) Revised Proposal Templates Detailed DD Report out DD Findings Report Issues and Assumptions Tracker Risk Management Plan DD Questionnaire and Data Collection Template DD Master Data Templates Statement of Work As is Process Assessment Questionnaire Guidelines Available SLA Guidelines

## Slide 6: Transition
Input | Output | Templates
RFP / response to RFP Contract / Letter of Intent/ SOW List of Assumptions –Technical and Commercial Presentations made during Bid Cycle Risk Log Customer Infrastructure/Application Baseline (list) Signed-off network infrastructure solution (Data and Voice) for Connectivity Job Descriptions & PAS details (if available) Transition Approach, Timelines & Resource Loading Planned Delivery Structure Tools to be Deployed and Integration solution Cost Sheet and Transition Budget (Transition and Steady State) Due Diligence Report | Signed SOW with SLA Signed-off Sales Handover Checklist Approved Master Transition Plan ITSM Scoping Document Approved Planning Phase Exit Checklist Approved Infrastructure Checklist Signed-off transition schedules (including communication plan and transition governance) Training Tracker Data Collection Templates customized and ready Infrastructure Setup Plan | Statement of Work SLA Contract Review Request for Information ITSM Process Scoping Master Transition Plan Boot Camp KAP Plan HR Transition Guidelines Available Business Process-Application Mapping Transition Models ITSM Process Scoping

## Slide 7: Knowledge Acquisition
Input | Output | Templates
Signed SOW with SLA Signed-off Sales Handover Checklist Approved Planning Phase Exit Checklist and Infrastructure checklist Signed-off transition schedules including communication plan and transition governance Finalized Tower Sequence for Transition Signed-off Meeting schedules for KAP ITSM Scoping Document and Training Tracker All resources required for KAP on board and Travel Plan for KAP resources All planned trainings conducted for the KAP resources Request for mail id creation submitted to the customer All Data Collection templates customized and ready Commencement of ODC Infrastructure set up and Network Infrastructure ordered Signed off tollgate/ exit criteria for all phases of transition (if not listed in SOW) | Updated Business Process Maps Updated Transition Plan Sign-off with customer team that planned knowledge transfer is complete Language Assessment done for Service Desk resources ODC Infrastructure ready All pre-process training (soft skill/ technical) complete Offshore/ Onsite Resource in place Secondary Support Plan Draft Service Delivery Plan | Boot Camp KAP Plan Data Collection Templates Tools Plan KAP Phase Exit Checklist

## Slide 8: Guided Support
Input | Output | Templates
KAP phase Completion Sign-off Secondary Support Plan Offshore/Onsite Resource in place Updated Transition Plan Updated Business Process Maps All pre-process training (soft skill/technical) complete ODC Infrastructure Ready Team having requisite ids created and access available | Sign-off Report formats/ templates Primary Support (Workload transition) plan week wise Agreed Ramp up SLA for Primary Support Daily dashboard report template with Contracted SLA and Primary Support Target SLA details Network infrastructure / Tools / Thin Client established and tested Final operations structure for the sub tower Secondary Support phase completion sign-off from customer. | ITSM Process Scoping Document Daily Dashboard Monthly Service Delivery Review Report Template Service Description Document Service Delivery Plan SLA –KPI Template Secondary Phase Exit Check List Guidelines Available ITSM process scoping document SLA definition Guidelines Service Desk Analyst Evaluation Guide Service Desk Voice Processing Guide

## Slide 9: Steady State
Input | Output | Templates
Signed-off Report formats/ templates Signed-off Guided Support phase completion from customer Primary Support (Workload transition) plan week wise Agreed Ramp up SLA for Primary Support Daily dashboard report template with Contracted SLA and Primary Support Target SLA details Final operations structure for the Network infrastructure / Tools | Reporting against metrics Submission of reports as per signed off formats Daily Operations Dashboard Ticket Audit Report Primary Support phase completion sign-off SLA performance against agreed Primary Support metrics Lessons Learnt Document Service Delivery Plan | Voice / Ticket Audit Template and Guidelines Lessons Learnt Primary Phase Exit Checklist Delivery Handover Checklist Customer Satisfaction Survey Form

## Slide 10: Transition Completion
Input | Output
Project Plan Exit Checklists of all the phases Open Action Item Tracker | Customer Satisfaction Survey The Transition Manager will do CSAT for the completed Transition Project within 2 weeks of Completion of project. All Documents collected and created during Transition should be filed in a structured manner with a Master list of Documents and document control. The Transition Manager should prepare a document that lists the lesson learnt during transition 30 days hand holding period Customer Sign-off at the end of each phase of the transition, formal sign off should be obtained from the customer that the deliverables of the phase has been met and that the transition can move to the next phase. Delivery Sign-off

## Slide 11: Transition Risk Management
Risk Management
Financial Management
Lack of skilled-resources deployment at appropriate time.
Scope breach due to understanding arbitration.
Lack of Communication plan or adherence to it.
Service Delivery escalations during Pilot/Guided support.
CAPEX escalation as against envisaged earlier
Customer Resources not available during transition.
Non-adherence to issue / escalation management.
Lack of co-operation due to Outsourcing/offshore backlash
Service Delivery Management
Schedule Management
Risk Identification
Risk Assessment & Analysis
Risk Mitigation Planning
Risk Tracking and Reporting
Possible Risks

## Slide 12: Transition Reporting & Tracking
Transition Effectiveness
Transition Project Tracking
Issue & Risk Management
Risk Management
All the identified risks are monitored for any escalation and auto-category wise correlation with issues.
Transition effectiveness to be tracked using completion percentage by towers.
CSAT
Auto-CSAT request shall be raised from the portal
Documentation Repository
All the transition project related documents, artifacts to be counter-checked for final sign-off.
All the transition project related activity at micro-breakdown work structure shall be monitored for completion status.
Exception reports and work completion report shall be created.
Issue Management
All the issues related to transition to be logged with priorities.
Issues logged shall have escalation mechanism
Daily/Weekly/Monthly reports to be generated especially for exception.

## Slide 13: Transition Registration / Administration Process-flow
Transition Initiation
Managed Services Team
Staffing Stream
Custom Projects
  Evaluate transition category.
  Assign Transition Project code.
  Register Transition in Portal.
  Process kick-off to completion for managed services
  Staffing ramp-up to completion.
  Custom Projects delivery upto the satisfaction of customer.

## Slide 14: Transition – Governance Structure
Responsibilities
Senior Management
Client Relationship Manager
Executive sponsors – COO and SBU head
Overall Responsibility
Transition Management Office
Service delivery lead
Operations
Module Supervisor
Transition Manager
Associates
Associates
Client Infra/ App
Client Infra/ App
Understand and deliver strategic objectives
Ensure management support
Act as final issue escalation point
Monitor streamlined Transition Service
Arbitrator between Delivery team and different functional group
Functional Groups
Admin Team
Training
Sourcing
Resource Engagement
Infrastructure Support
Security and Compliance

## Slide 15: Thank You